## Product Backlog
PRODUCT BACKLOG
|  |  |  | 0 | Note: Total LOC should be >= 720 * Number of project members |  |  |  | https://gitlab.com/swp3918810936
# | Function Name | Actor(Users) | Complexity | LOC | Planned Code Iteration | Student No | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration | LOC of IT1 | Comment 1 (Date: dd/MM/yyyyy) | % Add | LOC of IT2 | Comments 2 (Date: dd/MM/yyyyy) | % Add | LOC of IT3 | Comment 3 (Date: dd/MM/yyyyy) | % Add | LOC of IT4
1 | Register User | User, Admin | Medium |  | Iteration 1 | HE181370 | Mai Huy Hoàng | Iteration 1 | Done | Done | Done | Done | 100% | Iteration 1 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
2 | Authenticate User | User, Admin | Simple |  | Iteration 1 | HE181370 | Mai Huy Hoàng | Iteration 1 | Done | Done | Done | Done | 100% | Iteration 1
3 | Authorize User | User, Admin | Complex |  | Iteration 1 | HE181370 | Mai Huy Hoàng | Iteration 2 | Done | Done | Done | Done | 100% | Iteration 2
4 | Social Login | User | Medium |  | Iteration 2 | HE181370 | Mai Huy Hoàng | Iteration 2 | Done | Done | Done | Done | 100% | Iteration 2
5 | Forgot Password |  | Medium |  |  | HE182142 | Đỗ Hữu Sơn | Iteration 3 | Done | Done | Done | Done | 0 | Iteration 4 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
6 | Manage JWT / Session | User, Admin | Complex |  | Iteration 1 | HE181370 | Mai Huy Hoàng | Iteration 1 | Done | Done | Done | Done | 100% | Iteration 1 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
7 | Create Attachment | User | Complex |  | Iteration 2 | HE181370 | Mai Huy Hoàng | Iteration 4 | Doing | Doing | Doing | Doing | 20% | Iteration 4 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
8 | Delete Attachment | User | Complex |  | Iteration 2 | HE181370 | Mai Huy Hoàng | Iteration 2 | Doing | Doing | Done | Done | 80% | Iteration 4
9 | View Attachments | User, Admin | Medium |  | Iteration 2 | HE181370 | Mai Huy Hoàng | Iteration 2 | Doing | Doing | Doing | Doing |  | Iteration 4
10 | View Followings | User | Simple |  | Iteration 4 | HE181370 | Mai Huy Hoàng | Iteration 4 | Pending | Pending | Pending | Pending |  | Iteration 4
11 | View Followers | User | Simple |  | Iteration 4 | HE181370 | Mai Huy Hoàng | Iteration 4 | Pending | Pending | Pending | Pending |  | Iteration 4
12 | Follow/Unfollow Other User | User | Medium |  | Iteration 4 | HE181370 | Mai Huy Hoàng | Iteration 4 | Doing | Doing | Doing | Doing | 10% | Iteration 4
13 | Block/Unblock Other User | User | Medium |  | Iteration 4 | HE181370 | Mai Huy Hoàng | Iteration 4 | Pending | Pending | Pending | Pending |  | Iteration 4
14 | View Newsfeed Page | User | Medium |  | Iteration 1 | HE182090 | Nguyễn Tuấn Khanh | Iteration 1 | [6 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
15 | Create Post |  | Simple |  |  | HE182142 | Đỗ Hữu Sơn | Iteration 1 | Done | Done | Done | Done |  | Iteration 2 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
16 | View Post Details |  | Medium |  |  | HE182142 | Đỗ Hữu Sơn | Iteration 1 | Done | Done | Done | Done |  | Iteration 1 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
17 | Delete Comment | User | Medium |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3
18 | Add Comment | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3 | [6 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
19 | Like/Unlike Comment | User | Medium |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3 | [6 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
20 | Reply Comment | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3
21 | View Comments List | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3 | [6 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
22 | View Users liked Post | User |  |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 1 | [5 empty] | Final
23 | View Explore Post List | User |  |  |  | HE182090 | Nguyễn Tuấn Khanh
24 | View Profile Page |  | Medium |  | Iteration 3 | HE182142 | Đỗ Hữu Sơn | Iteration 1 | Done | Done | Done | Done | 50% | Final
25 | Edit Profile |  | Simple |  | Iteration 3 | HE180030 | Trần Xuân Hoàn | Iteration 1 | Completed | Completed | Completed | Completed | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
26 | Send notifications |  | Medium |  | Iteration 2 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Done | Done | Done | Done | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
27 | View notifications (time grouped) |  | Simple |  | Iteration 2 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Done | Done | Done | Done | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
28 | Mark notifications as read |  | Simple |  | Iteration 2 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Done | Done | Done | Done | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
29 | Process notifications event |  | Medium |  | Iteration 2 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Done | Done | Done | Done | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
30 | Receive notifications in real time |  | Complex |  | Iteration 2 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Done | Done | Done | Done | 100% | Iteration 3 | 0
31 | Search (user) |  | Simple |  | Iteration 2 | HE180030 | Trần Xuân Hoàn | Iteration 2 | Completed | Completed | Completed | Completed | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
32 | Edit users setting |  | Simple |  | Iteration 1 | HE180030 | Trần Xuân Hoàn | Iteration 1 | Completed | Completed | Completed | Completed | 100% | Iteration 3 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
33 | Sent real-time message | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3
34 | Receive real-time message | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 3
35 | View Box Chat | User | Medium |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 1
36 | View Conversation List | User | Medium |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 1
37 | Create Conversation | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 1
38 | Delete Converstation | User | Complex |  |  | HE182090 | Nguyễn Tuấn Khanh | Iteration 1
39 | View activity history - liked posts |  | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 20%
40 | View activity history - comments |  | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 20%
41 | View users | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 20%
42 | View user's detail profile | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 70%
43 | Add new user | Admin | Medium |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 30%
44 | Edit user role | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 60% |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
45 | Assign role to users | Admin | Medium |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 20%
46 | Toggle user status | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 60% |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
47 | View roles & permissions | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 60% |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
48 | Add a role | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 50% |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
49 | Modify existing roles | Admin | Simple |  | Iteration 3 | HE186182 | Lâm Tiến Thăng | Iteration 3 | Doing | Doing | Doing | Doing | 50% |  | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
50 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
51 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
52 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
53 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
54
55
56 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
57 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
58 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
59
60 | [14 empty] | 0 |  | 0 | #REF! |  |  | #REF! |  |  | #REF!
61 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
62 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
63 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
64 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
65 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
66 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
67 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
68 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
69 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
70 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
71 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
72 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
73 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
74 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
75 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
76 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
77 | [14 empty] | 0 |  | 0 | 0 |  |  | 0 |  |  | 0
| Total LOC | [13 empty] | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!
| Graded for codes (180 LOC for 1 Iteration) | [13 empty] | 0 |  |  | #REF! |  |  | #REF! |  |  | #REF!

## Estimate LOC GuideLine
Below are some guidelines for LOC estimation for UC/function
1 | Edit & Create/Add New Use cases/function is normally is medium, number of LOCs of the UC can be caluclated as below
a) If the application will be developed in Java (JSP & Servlet) and use MVC II architecture model
|  |  | 1 | input field | LOC will be calculated | 15 | LOC
LOC of UC = Number of input fields * LOC/1 input field
E.g. If UC/function has 10 input fields, the LOC of this UC will be 12*10LOC
|  |  | 12 | input field |  | 180 | LOC
a) If the application will be developed in .NET and use MVC II architecture model
|  |  | 1 | input field | LOC will be calculated | 10 | LOC
2 | Delete/Update Status function/UC
LOC of this function will be calculated less than 20LOC if this are no complex in checking constraints
3 | View/List with no filter condition function
Number of LOCs of these functions will be calculated same with the edit/add new function
|  |  | 1 | output field | LOC will be calculated | 5 | LOC
4 | Search function: Number of LOC will be calculated by number of output fields and number of input fields (search conditions)
Notes
LOC parameter defined for each field based on assumption that the validation data and logic process are not complex
If Codes is generated by tools, the number of LOC is smaller
4